Midwife E-Learning Project
Terms of Reference to develop module 1 - maternal nutrition

May 2025

Start date:  ASAP

Fixed-term contract Length:  6-months from 1st May

Daily Rate:  To be agreed as per consultant rate

Purpose:

To develop and pilot and e-learning module for the midwife training programme to strengthen the effectiveness of the Action for Development Midwife training framework

Key deliverables:

- Procure effective e-learning software programme that can be used to implement midwife e-learning programme

- Develop and test 45 min - 1.5-hour maternal nutrition training session for midwives.

- Translate e-learning materials into Persian

- Complete an end of project report to summarise learning and recommendations for other midwife training modules

Work Assignment:

- Develop the maternal nutrition course content of a 2.5-hour training session for midwives.  Key topics to cover include:

- Why Nutrition Matters

- Role of Midwives in Nutrition

- Healthy Eating during pregnancy and breastfeeding

- Why breastfeeding is important

- Breastfeeding in the first hour

- Breastfeeding techniques

- Common breastfeeding challenges

- Monitoring Mother and Baby

- Hand hygiene

- Procure an effective e-learning software programme that can be used by midwives through mobile technology.  Please note: The software must be:

  - Easily accessible through basic mobile technology operated in resource-constrained areas

  - Able to be readily translated into Persian.

  - Able to monitor numbers of midwives who complete the training

  - Include a pre-post knowledge test to determine effectiveness of training

  - Total value available to procure software and licence fee is up to $1850

- Ensure translation of materials into Persian

- Work with Midwife Training Coordinator in Kabul to test pilot e-learning modules in Kabul and Takhar provinces

- Create a detailed training and implementation plan to support project roll-out.  Please note: $20 sim-top up cards are available for up to 80 midwives participating in the training.

- Evaluate the effectiveness of the e-learning pilot and make recommendations for roll-out in an end of project report (due 7-months after start date)